## Oct
DILG-PS FORM 008
REGIONAL MONTHLY ACTIVITY TRACKING REPORT
For the Month Ending _________ 2019
NAME OF REGIONAL OFFICE: DILG RIV-A
Projects/Activities |  |  |  | Performance Indicators | PHYSICAL AND FINANCIAL REQUIREMENTS (3) |  | PHYSICAL AND FINANCIAL ACCOMPLISHMENTS (4) |  | Reason/s for not conducting the planned activity | REMARKS
[5 empty] | PHYSICAL TARGET | PROGRAMMED AMT. | ACTUAL ACCOMPLISHMENT | AMOUNT DISBURSED |  | (Indicate if: (a) reset to a later date; (b) replaced by a new activity or © not to be conducted anymore)
(1) |  |  |  | (2) | (3.1) | (3.2) | (4.1) | (4.2) | (5) | (6)
TOTAL LOCALLY FUNDED PROJECTS |  |  |  |  | 0
TOTAL LGA FUNDED PROJECTS
1. ACCOUNTABLE, TRANSPARENT, PARTICIPATIVE
AND EFFECTIVE LOCAL GOVERNANCE
SUB TOTAL LOCALLY FUNDED PROJECTS
SUB TOTAL LGA FUNDED PROJECTS
1.2. LGPMS - SEAL OF GOOD LOCAL
GOVERNANCE (SGLG)
LOCAL FUND
|  | 1.2.6. National Calibration |  | No. of activities attended
|  | 1.2.7. SGLG Conferment |  | % of qualified LGUs conferred with 2017 SGLG
|  | 1.2.8. Coordination Meeting |  | No. of meetings conducted
|  | 1.2.10. Other Related Activities |  | No. of activities conducted/ attended
2. PEACEFUL, ORDERLY AND SAFE LGUs
SUB TOTAL LOCALLY FUNDED PROJECTS
SUB TOTAL LGA FUNDED PROJECTS
3. SOCIALLY PROTECTIVE LGUs
SUB TOTAL LOCALLY FUNDED PROJECTS
SUB TOTAL LGA FUNDED PROJECTS
4. ENVIRONMENT PROTECTIVE, DISASTER
RESILIENT AND CLIMATE
CHANGE ADAPTIVE LGUs
SUB TOTAL LOCALLY FUNDED PROJECTS
SUB TOTAL LGA FUNDED PROJECTS
5. BUSINESS-FRIENDLY AND COMPETITIVE LGUs
SUB TOTAL LOCALLY FUNDED PROJECTS
SUB TOTAL LGA FUNDED PROJECTS
6. STRENGTHENED INTERNAL | [10 empty] | 0 | 0 | #REF!
| ORGANIZATIONAL CAPACITY | [9 empty] | 0 | 0 |  | FAD
SUB TOTAL LOCALLY FUNDED PROJECTS
SUB TOTAL LGA FUNDED PROJECTS
Prepared and submitted by: | [5 empty] | Noted by: |  |  |  | APPROVED BY:
Name & Signature of |  |  |  | Name & Signature of |  | Name & Signature of |  |  |  | Name & Signature of
Regl. /Designated Planning Officer |  |  |  | Accountant/ Disbursing Officer |  | Chief Admin. Officer/ Senior Staff |  |  |  | Regional/ Provincial Director
NOTE: Data/information entered in columns 1, 2, 3.1 and 3.2 should be the same as those reflected in the Monthly Activity Action Plan for a particular month.

## INSTRUCTIONS
Column 1 | - | Activities–List the work/actions/tasks to be conducted or implemented by the bureau/PMO/service/office through which inputs such as funds, manpower and other types of resources are mobilized to produce specific outputs/deliverables.
Column 2 | - | Performance Indicator – Indicate here the quantitative or qualitative factor or variable that provides a simple and reliable means to measure accomplishments.
Column 3 | - | Physical and Financial Requirements – refer to the physical units and funds needed to implement/accomplish the planned activities for the period August, September, October, November & December.
Column 3.1 | - | Physical Targets - Indicate the quantitative unit of work measurement of the based on the key performance indicator per planned activity for a particular month.
Column 3.2 | - | Programmed Amount – Indicate the funds needed to implement the activity for a particular month.
Note: Columns 1, 2, 3, 3.1 and 3.2 should be extracted by Regional Office in their submitted Monthly Activity Action Plan .
Column 4 | - | Physical and Financial Accomplishments– refer to the physical units and funds implemented/accomplished by the office.
Column 4.1 | - | Actual Physical Accomplishments - Indicate the actual accomplishment based on the physical targets given in Column 3.1.
Column 4.2 | - | Amount Disbursed – Indicate the estimated actual expenses spent vis-à-vis the programmed amount indicated in column 3.3.
Column 5 | - | Reason/s for not conducting the planned activity – Indicate here the reasons/justifications for not implementing or conducting the planned activity.
Column 6 | - | Remarks - Indicate in this column if : (a) reset to a later date; (b) replaced by a new activity or (c) not to be conducted anymore.
INSTRUCTIONS IN FILLING-UP DILG-PS FORM 008: REGIONAL MONTHLY ACTIVITY TRACKING REPORT
This form shall be used in monitoring and tracking the monthly physical accomplishments (physical performance) and utilization of funds (financial performance) of regionally managed activities of the bureaus/PMOs/services/offices including the reason/s for not conducting the planned activity and indicate whether the activity will be reset to a later date, replaced by a new activity or not to be conducted anymore.
Coverage: Physical and financial accomplishments up to the last working day of each month
Deadline of Submission: On or before the 15th working day of the ensuing month, i.e., starting this September 15, 2018. Cut-off date of report will be at the end of each month.
Responsible Person : Regional Planning Officer in close partnership/coordination with Project Focal Persons and Regional Budget Officer/ Accountant
Definition of Entries:
For the Month ending – Indicate the reporting month.
Name of Regional Office – Indicate the name of the Regional Office.
This accomplished form must be signed by the Regional Planning Officer and the Accountat who prepared the report, noted by the Chief Administrative Officer and approved by the Regional Director.

## Overall
DILG-PS FORM 008
REGIONAL MONTHLY ACTIVITY TRACKING REPORT
For the Month Ending AUGUST 2018
NAME OF REGIONAL OFFICE: DILG RIV-A
Projects/Activities |  |  |  | Performance Indicators | PHYSICAL AND FINANCIAL REQUIREMENTS (3) |  | PHYSICAL AND FINANCIAL ACCOMPLISHMENTS (4) |  | Reason/s for not conducting the planned activity | REMARKS
[5 empty] | PHYSICAL TARGET | PROGRAMMED AMT. | ACTUAL ACCOMPLISH-MENT | AMOUNT DISBURSED |  | (Indicate if: (a) reset to a later date; (b) replaced by a new activity or © not to be conducted anymore)
(1) |  |  |  | (2) | (3.1) | (3.2) | (4.1) | (4.2) | (5) | (6)
TOTAL LOCALLY FUNDED PROJECTS |  |  |  |  | 4149.75 | 12682296.1 | 103 | 13532722.07
TOTAL LGA FUNDED PROJECTS |  |  |  |  | 0 | 0 | 1 | 21000
1. ACCOUNTABLE, TRANSPARENT, PARTICIPATIVE
AND EFFECTIVE LOCAL GOVERNANCE |  |  |  |  | 8 | 1884000 | 76 | 2589410
| 1.2. LGPMS - SEAL OF GOOD LOCAL |  |  |  | 0 | 0 | 68 | 265000
GOVERNANCE (SGLG)
1.2.10. Other Related Activities
|  |  | National Validation | No. of regions validated |  |  | 68 | 265000 |  | R2 (35 LGUs) and RIV-A (33 LGUs)
| 1.3. PERFORMANCE CHALLENGE FUND (PCF) |  |  |  | 0 | 0 | 0 | 493250
1.3.7. Other Related Activities
|  |  | - payment for 26-29 June Consultative | No. of activities conducted/ attended |  |  |  | 493250
Conference with National and Regional PCF
Teams on PCF Implementation
| 1.4. CSO PEOPLE'S PARTICIPATION | [6 empty] | 82160
PARTNERSHIP PROGRAM (CSO PPPP)
|  | 1.4.5. Conduct of Utilization Conferences: |  | No. of LGUs that conducted
|  |  | - Downloading of Funds for Ucs for CSIS | Utlization Conferences :
|  |  | Phase 1 and Improving Participation in | - Magallanes |  |  |  | 41080
|  |  | Phase 1 and Improving Participation in | - Pagbilao |  |  |  | 41080
|  |  | Local Investment Programming and Local | - Pagsanjan |  |  |  | 53700
Planning Process Phase II
1.4.8. Other Related Activities:
|  |  | - payment for the conduct of the Training | No. of activities conducted |  | 236595 |  | 236595
on Improving Citizen Participation in Local
Investment Programming and Local
Planning Process
- payment for the Consultative Meeting on
|  |  | the Status of CY 2018 CSIS Implementation | No. of activities conducted |  | 8800 |  | 8800 | LF
on 01/06/2018
| 1.5. LUPONG TAGAPAMAYAPA INCENTIVES | [7 empty] | LGMED
|  | AND AWARDS (LTIA) |  |  | 6 | 284000 | 6 | 284000
1.5.2 Assessment and Validation of Provincial
Nominees per category
|  |  | 1.5.2.1. LTIA 2018 National | [6 empty] | 01 - 03 August (LF (Sub Allotment No.
|  |  | Field Validation | No. of assessment conducted/ assisted | 1 | 84000 | 1 | 84000 | LF | 2018-06-0871)_
|  | 1.5.3 Submission of nomination documents |  | No. of Regional Lupon nominees | 4 |  | 4 |  | LF | Final Assessment of LTIA Entries
|  | of Lupons (Regional winner) |  | assessed and evaluated | [5 empty] | and Deliberation of Regional Winners
1.5.4. Conferment of Awards
|  |  | (Regional Level) | No. of activities conducted | 1 | 200000 | 1 | 200000 | LF | awarded on July 25
| 1.11.BARANGAY NEWLY ELECTED OFFICIALS | [7 empty] | LGCDD
|  | (BNEO) PROGRAM |  |  | 2 | 1600000 | 2 | 1465000
|  | 1.11.1. Coordination Meeting |  | No. of meeting conducted/attended | 1 | 100000 | 1 | 20900 |  | 19 July Preparatory Meeting
|  | 1.11.2. 'Barangay Newly Elected Officials | [7 empty] | July 30- August 1
(BNEO) towardsGrassroots Renewal
and Empowerment for Accountable
and Transparent Barangays (GREAT)
Enhancement and Walkthrough
|  |  | Seminar for DILG Officers in RIV-A | No. of activities conducted | 1 | 1500000 | 1 | 1444100 |  | 30 July - 01 August
2. PEACEFUL, ORDERLY AND SAFE LGUs |  |  |  |  | 11.75 | 6956487.6 | 1 | 7141238.07
2.1. SUSTAINING THE EFFECTIVENESS OF
SUB-NATIONAL PEACE AND
|  | ORDER COUNCILS |  |  | 1 | 247500 | 0 | 14000
| 2.1.2. Regional Peace and Order Council (RPOC) |  |  | No. of meetings conducted | 1 | 247500
- payment for the conduct of the Joint
RPOC -Executive Committee Meeting for
RIV-A & MIMAROPA on June 14
| 2.1.3. Nationwide Roll-out re: Orientation on the |  |  | No. of activities conducted/ attended | [5 empty] | -
POCs Performance Audits
| 2.1.4. Support to Operations |  |  | TEVs for POC Performance Audit TOT |  |  |  | 14000
| 2.2. STRENGTHENING OF LOCAL ANTI DRUG | [7 empty] | LGMED
|  | ABUSE COUNCILS (LADACS) |  |  | 1368 | 201820 | 2 | 0
2.2.1. Strengthening Anti-Drug Abuse Council
|  |  | Training of Trainers | No. of activities conducted | 5
|  | 2.2.2. Roll-Out Training on Strengthening |  | No. of activities conducted | 5
|  |  | Anti-Drug Abuse Councils | No. barangays with BADAC | 1356
|  | 2.2.8. Support to Operations |  | Hiring of Staff:
|  |  |  | -Program Officer (SG12) | 1 | 69000 | 1
|  |  |  | -Program Officer (SG12) | 1 | 69000 | 1
|  |  |  | Travelling |  | 30487
|  |  |  | Supplies |  | 33333
2.3. SUPPORT TO PEOPLE'S LAW
|  | ENFORCEMENT BOARDS (PLEBS) |  |  | 6 | 4543200 | 1 | 7127238.07
2.3.1. Regional Training of Trainers on the
PLEB Online Database System (PODS) &
|  |  | and PLEB Legal Skills Enhancement | No. of activities conducted | 1 | 1476000 | 1 | 1476000
2.3.2. Roll-Out Of PLEB Online Database System
|  | and PLEB Legal Skills Enhancement |  | No. of activities conducted | 5 | 3067200 |  | 3067200 |  | July to October
2.3.4. Support to Operations
|  |  | - For the payment of salary of PLEB Program |  |  |  |  | 604038.07
Management Teams and Special PLEB
Provincial Coordinators
|  |  | - To cover subsidy assistance for the provision |  |  |  |  | 1980000
of per diem to PLEB members:
|  | 2.3.5. Support to Operations |  | Hiring of Staff:
|  |  |  | -Program Officer (SG_) |  |  | 1
|  |  |  | -Program Officer (SG_) |  |  | 1
| 2.4. ENHANCED COMPREHENSIVE LOCAL | [8 empty] | AWAITING GUIDELINES FROM CO
|  | INTEGRATION PROGRAM (E-CLIP) |  |  | 0.75 | 1632000 | 0 | 0
|  | 2.4.1. Facilitation of Processing of Request |  | 100% of requests for financial assistance | 0.75 | 1632000 |  |  |  | as Stand by fund on surfacing efforts
|  | for Provision of Financial Assistance |  | verified and processed: | [5 empty] | for FRs
|  | to Former Rebel (FR) and Receiving |  | - Immediate Assistance
|  | Unit |  | - Livelihood Assistance
- Reintegration Assistance
- Firearms Renumeation to FR's turned-in Firearms
2.5. NATIONAL ADVOCACY FOR THE
PREVENTION OF ILLEGAL DRUGS,
CRIMINALITY, CORRUPTION AND
VIOLENT EXTREMISM
|  | 2.5.1. BANTAY KORUPSYON |  |  | 4 | 533787.6 | 0 | 0 | 0 | AWAITING GUIDELINES FROM CO
2.7.1. Support to Operations
Hiring of Staff:
|  |  |  | - Legal Officer (SG22) | 1 | 158349
|  |  |  | - Legal Officer (SG22) | 1 | 158349
|  |  |  | - Regional Head Coordinator (SG13) | 1 | 72672
[6 empty] | 4844.8 |  |  |  | payment of 26-29 June services
|  |  |  | - Regional Assistant Coordinator (SG11) | 1 | 60537
[6 empty] | 4035.8 |  |  |  | payment of 26-29 June services
|  |  |  | Travelling |  | 10000
|  |  |  | Communication Expenses |  | 5000
|  |  |  | Supplies |  | 30000
|  |  |  | Utilities |  | 30000
3. SOCIALLY PROTECTIVE LGUs |  |  |  |  | 4038 | 2351238.5 | 11 | 3131015
| 3.1. GENDER AND DEVELOPMENT (GAD) |  |  |  | 1 | 30000 | 1 | 30000 | LGMED
3.1.2. Child-Friendly Local Governance
Audit (CFLGA) LGU Assessment
|  |  | 3.1.2.1. Regional Table Top Assessment | No. of activities conducted | 1 | 30000 | 1 | 30000 |  | 23 & 24 August
| 3.2. SUPPORT TO LOCAL GOVERNANCE | [7 empty] | LGMED
|  | PROGRAM (SLGP) |  |  | 1 | 180000 | 1 | 409195
|  | 3.2.1. Improvement of the Local Investment |  | No. of LDIP and Provincial Dev't.
|  | Programming and Budgeting and |  | Plan (PDP) and Sustainable |  |  |  | 229195 |  | Transfer of funds for Local Investment
|  | Local Planning Process |  | Dev't. Goals (SDG) reviewed and localized | [5 empty] | Programming & Local Planning Process
|  | 3.2.2. Establishment and Operationalization |  | No. of ADM Platform Users' Training | [5 empty] | Conducted on June 18-22 in
|  | ADM Platform Users' Training |  | conducted/attended | [5 empty] | LGUs of Laguna:
3.2.3. Post Assessment Monitoring and
Evaluation on the Gender
|  |  | Responsiveness of PPAs Cum | No. of related activities
|  |  | Orientation on the AM FY 2018 Program | conducted/ attended | 1 | 180000 | 1 | 180000 | LF | 02 & 03 August
|  | 3.2.4. Other Related Activities |  | No. of related activities provided with TAs
No. of related activities conducted/ attended
| 3.4. SUSTAINABLE DEVELOPMENT GOALS (SDG) |  |  |  | 1 | 0 | 0 | 0 | LGCDD
|  | 3.4.3. Other Related Activities |  | No. of activities conducted/ attended | 1
| 3.5. SALINTUBIG |  |  |  | 10 | 42900 | 1 | 42900 | LGMED
|  | 3.5.1. Provision of 2018 Financial Subsidy |  | No. of LGUs provided with subsidy | 8 |  |  |  |  | - LGUs Endorsed to DILG-CO-OPDS for
endorsement to DBM: General Nakar,
Paete and San Juan
- as per recent guidelines, DILG shall endorse
LGU required documents to the DBM. DBM is
responsible in providing subsidy to the LGUs
|  | 3.5.3. Support to Operations |  | Travelling |  |  |  |  | LF
Communication
|  | 3.5.4. Other Related Activities |  | No. of activities conducted | 1 |  |  |  |  | 1. (Feb. 12-14) SALINTUBIG Island-Wide
Stakeholders Assessment Workshop at Hive
3.5.4. Related Activities
|  |  | - payment for the Mid – Year Evaluation | No. of activity conducted/ attended | 1 | 42900 | 1 | 42900 | LF
Meeting for the Implementation of LFPs
| 3.6. ASSISTANCE TO MUNICIPALITIES |  |  |  | 2 | 510000 | 1 | 53750
|  | 3.6.3. Coordination Meetings |  | no. of meetings conducted/ attended | 1 | 18500 | 1 | 18500 | LF | Coordination Meeting for the Monitoring of ADM
FY 2017 & 2018 Projects on 3Q
|  |  | - Payment for the conduct of Coordination Meeting |  |  | 35250 |  | 35250 | LF
and Preparation for the Implementation of
Assistance to Municipalities (AM) 2018 Cum
Conditional Matching Grant to Provinces (CMGP)
Status Implementation Update
|  | 3.6.4. Support to Operations |  | No. of activities conducted | 1 | 96250
|  |  |  | Supplies |  | 90000 |  |  | LF
|  |  |  | Travelling |  | 170000 |  |  | LF
|  |  |  | Communication |  | 100000 |  |  | LF
Salaries of Hired Personnel and Support to
Operations for the Activities of
OPDS Locally-funded Projects
ADM-OPMO Regional and Provincial
Team Cost of Services, Coordination
Activities and Mobilization Support
| 3.7. TRANSITION TO FEDERALISM |  |  |  | 4023 | 1588338.5 | 2 | 204530 |  | LGCDD
|  | 3.7.1. Production of IEC Materials |  | No. of LGUs provided with IEC materials | 4018 | 1242567
|  |  |  | No. of meetings conducted/ attended | 1
3.7.2. Federalism Roadshow
3.7.2. 1. Federalism Coordination
|  |  | Meetings | No. of meetings conducted/ attended | 1 | 77983.5
|  | 3.7.3. Hiring of Regional Program Officers |  | No. of personnel hired:
|  |  |  | -Regional Project Manager (Php 35,693.00) | 1 | 35693 | 1
|  |  |  | - Provincial Coordinator (Php 27,565.00) | 1 | 27565 | 1
|  | 3.7.4. Related Activities |  | No. of related activities conducted/ attended | 1
|  |  | - payment for the conduct of the 19-21 June |  |  | 204530 |  | 204530
Strategic Planning Workshop on Federalism
3.8. PRESIDENT'S DIALOGUE FOR BARANGAY
|  | GOOD GOVERNANCE: 14 June |  | No. of PLGUs attended |  |  | 5 | 2390640 | LF
4. ENVIRONMENT PROTECTIVE, DISASTER
RESILIENT AND CLIMATE
| CHANGE ADAPTIVE LGUs |  |  |  | 85 | 303918 | 12 | 30600
| 4.2. MANILA BAY CLEAN-UP, REHABILITATION | [8 empty] | LGCDD
|  | AND PRESERVATION PROGRAM (MBCRPP) |  |  | 85 | 303918 | 12 | 30600
4.2.5 KPI 6: Information, Education and
Communication (IEC) Campaigns
|  |  | 4.2.5.1. Partnership with LGUs in | No. of activities conducted | 2 | 20000 | 2 | 18000 |  | \
|  |  | support to Manila Bayanihan | No. of LGUs partnered with | 2 |  | 2
Clean-ups:
4.2.6. Project Monitoring Office (PMO):
|  |  | 4.2.6.2. MBRTG Quarterly Meetings | No. of meetings conducted | 1 | 30000 | 1 | 12600 | LF | 2018-08-14
|  |  | 4.2.6.3. M & E of LGUs using | No. of Workshop and Orientation conducted | 1
|  |  | Compliance Score Sheet | No. of LGU Compliance Score Sheets consolidated | 67
|  |  |  | No. of RIAC Meetings conducted | 1
|  |  |  | No. of Roll-out cum Utilization Conference conducted | 3
No. of related activity conducted/attended
|  | 4.2.7. Support to Operations: |  | No. of Staff & Personnel hired: |  |  |  |  | LF
|  |  |  | -Program Officer (SG12) | 1 | 26139.67 | 1
|  |  |  | -Program Officer (SG12) | 1 | 26139.67 | 1
|  |  |  | -Program Officer (SG12) | 1 | 26139.67 | 1
|  |  |  | -Program Officer (SG12) | 1 | 26139.67 | 1
|  |  |  | -Program Officer (SG14) | 1 | 21387 | 1
|  |  |  | -Program Officer (SG12) | 1 | 26139.67 | 1
|  |  |  | -Program Officer (SG12) | 1 | 26139.67 | 1
|  |  |  | Travelling and Communication Expenses |  | 25000 |  |  | LF
|  |  |  | Supplies and Materials: |  | 25000 |  |  | LF
|  | 4.2.8. Related Activities |  | No. of related activity conducted/attended | 1 | 25692.98
5. BUSINESS-FRIENDLY AND COMPETITIVE LGUs |  |  |  |  | 7 | 1186652 | 3 | 640459
5.3. IMPROVED LGU COMPETITIVENESS AND
EASE OF DOING BUSINESS (Component 1:
LGU Public-Private Partnership for the
| People Inivitiative for Local Government (P4) |  |  |  | 4 | 270666 | 1 | 28814
|  | 5.3.4. Training on Enhanced Feasibility |  | No. of trainings conducted | 1 | 265480
Study (LGU P4: Writeshop/Workshop on
the Preparation of Enhanced Feasibility Study)
|  |  | 5.3.4.1. Related Consultation Meeting | No. of activities conducted | 1 |  | 1 | 7000 |  | 2018-08-20
|  | 5.3.5. Monitoring, Mentoring and Provision |  | No. of LEIPOs Forum cum Business Matching | 1
|  |  | of TA on PPP | Enhanced Feasibility conducted/ attended
|  |  |  | No. of technical assistance/ communication provided | 1
|  |  |  | Travelling and other Related Expenses |  | 5186 |  |  | LF
5.3.6. Support to Operations
|  |  | TEVs for the Conduct of Regional Consultation |  |  |  |  | 21814
and Progress monitoring on the
implementation of P4
| 5.3. IMPROVED LGU COMPETITIVENESS AND | [8 empty] | Awaiting final plan and targets
| EASE OF DOING BUSINESS (Component 2: | [8 empty] | from DILG CO
| Streamlining of Construction Permitting) |  |  |  | 2 | 435986 | 2 | 611645
5.3.1. (2.1. BPLS)
5.3.1.1. Development of Policies in
Support to Streamlining BPLS
|  |  | 5.3.1.1.1. BPLS Automation/ | No. of related consultation / dialogue/
|  |  | Computerization | workshop/ meeting attended |  |  | 1 | 244645
|  |  | - payment for the Coaching and Mentoring of LGUs |  |  | 329200 |  | 329200
|  |  | on BPLS Automation/ Computerization cum | [5 empty] | LF
E-BPLS User Training 2018 on June 19-21
5.3.1.1.2. Manual in Implementing the
|  |  | Revised Standard in | No. of related consultation / dialogue/ | [5 empty] | on 17 July
|  |  | Processing BPLS in all C/Ms | workshop/ meeting attended
5.3.4. Focus Group Discussion (FGD) on
the Integration of Barangay
Clearance in LGU Permitting
|  |  | Process | No. of related activity conducted | 1 | 37800 | 1 | 37800 | LF | on 17 July
|  | 5.3.5. Other Related Activities |  | No. of activities conducted/ attended | 1 | 68986
| 5.5. SUPPORT TO CONDITIONAL MATCHING | [7 empty] | LF | LGMED
| GRANT TO PROVINCES (CMGP) |  |  |  | 1 | 480000 | 0 | 0
5.5.5. Support to Operations
|  |  |  | No. of related- activities conducted | 1 | 295000 |  |  | LF
|  |  |  | Supplies |  | 65000 |  |  | LF
|  |  |  | Travelling |  | 75000 |  |  | LF
|  |  |  | Communication |  | 45000 |  |  | LF
6. STRENGTHENED INTERNAL |  |  |  |  | 0 | [7 empty] | 0 | [8 empty] | 0 |  |  | #REF!
| ORGANIZATIONAL CAPACITY |  |  |  | 0 | [7 empty] | 0 | [8 empty] | 0 |  |  |  | FAD
| LGA Fund |  |  |  | 0 | 0 | 1 | 21000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6.11. LOCAL GOVERNANCE REGIONAL | [11 empty] | 0 | [8 empty] | 0
|  | RESOURCE CENTER (LGRRC) | [10 empty] | 0 | [8 empty] | 0 |  |  | #REF!
|  | 6.11.5. Training on the Enhancing LGU | [19 empty] | 0 | LGCDD | Awaiting result of the related-Competency
|  |  | Capacity on Planning | [18 empty] | 0 |  | Assessment
|  |  | 6.11.5. Competency Assessment Tool | No. of related activities conducted |  |  | 1 | 21000 | 1 | 2018-08-23 | 1 | 1 | [9 empty] | 0 | LGCDD
|  |  | Administration Exit Conference cum Regional | [18 empty] | 0
|  |  | Coordination Meeting For Enhancing LGU | [15 empty] | 42750 |  |  | 42750 |  | LGA Fund
|  |  | Capacity on Planning and Implementation of LDPs | [15 empty] | 42750 |  |  | 42750 |  | LGA Fund
Prepared and submitted by: | [5 empty] | Noted by: |  |  |  | APPROVED BY:
___________________________ | ANGELIQUE MEI A. IDLAO |  |  | RESTITUTO B. NAÑEZ, III |  | ATTY. JORDAN V. NADAL |  |  |  | MANUEL Q. GOTIS, CESO III
Name & Signature of |  |  |  | Name & Signature of |  | Name & Signature of |  |  |  | Name & Signature of
Regl. Planning Officer |  |  |  | Accountant |  | Chief Admin. Officer |  |  |  | Regional Director
NOTE: Data/information entered in columns 1, 2, 3.1 and 3.2 should be the same as those reflected in the Monthly Activity Action Plan for a particular month.